## WARD1
Ward 1 FY 23
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
WATER STREET | SHANDEL DR | UNION ST | 2022 - COMPLETE | Poor | Mill & Overlay | 761.9591 | 0.14431 | 59 | NA | NA | 22750
WATER STREET | UNION ST | GOODWINS AVE | 2022 - COMPLETE | Fair | Mill & Overlay | 552.1403 | 0.10457 | 67 | NA | NA | 22750
WATER STREET | GOODWINS AVE | WOODWELL AVE | 2022 - COMPLETE | Fair | Mill & Overlay | 405.0962 | 0.076723 | 63 | NA | NA | 22750
WATER STREET | WOODWELL AVE | MARLBORO ST | 2022 - COMPLETE | Poor | Mill & Overlay | 274.4776 | 0.051984 | 59 | NA | NA | 22750
ALTER COURT | BARTON ST | DEAD END | 2022 - COMPLETE | Poor | Reclamation | 179.2454 | 0.033948 | 29 | TBD | Asphalt | 22800
BARTON COURT | BARTON ST | DEAD END | 2022 - COMPLETE | Poor | Reclamation | 203.9173 | 0.038621 | 10 | TBD | Asphalt | 32600
BARTON STREET | ALTER CT | BARTON CT | 2022 - COMPLETE | Poor | Reclamation | 250.804 | 0.047501 | 6 | TBD | Asphalt | 40600
| BARTON CT | CHESTNUT ST | 2022 - COMPLETE | Poor | Reclamation | 260.7549 | 0.049385 | 6 | TBD | Asphalt | 40600
| HIGH ST | ALTER CT | 2022 - COMPLETE | Poor | Reclamation | 395.9725 | 0.074995 | 20 | TBD | Asphalt | 40600
GOODWINS AVE | UNION ST | WATER ST | 2022 - COMPLETE | Very Poor | Reclamation | 179.2186 | 0.033943 | 5 | NA | NA | 12000
MILK ST | FRANKLIN ST | BROMFIELD ST | 2022 - COMPLETE | Very Poor | Reclamation | 264.2843 | 0.050054 | 38 | NA | NA | 31666.6667
| FEDERAL ST | LIME ST | 2022 - COMPLETE | Poor | Reclamation | 612.1002 | 0.11593 | 59 | TBD | TBD | 168627.525
| LIME ST | FRANKLIN ST | 2022 - COMPLETE | Very Poor | Reclamation | 501.8944 | 0.095056 | 37 | TBD | TBD | 105745.4665
[8 empty] | TOTAL |  |  | 311866.6667
Ward 1 FY 25
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
HIGH ST E | BROMFIELD ST | BARTON ST | 2024 | Poor | Mill & Overlay | 308.3574 | 0.058401 | 52 | 2023 | TBD | 18633.0115
FEDERAL STREET | HIGH ST | WATER ST | 2024 | Very Poor | Reclamation | 2085.7 | 0.32 | 27 | 2023 | TBD | 300000
LANCASTER ROAD | SHANDEL DR | CUL DE SAC | 2024 | Poor | Mill & Overlay | 274.1129 | 0.051915 | 66 | 2023 | TBD | 17944.0415
SMITH'S STREET | BECK ST | WATER ST | 2024 | Poor | Reclamation | 575.3742 | 0.10897 | 33 | 2023 | TBD | 104308.9431
[8 empty] | TOTAL |  |  | 440885.9961
Ward 1 FY 27
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
LUNT STREET | PURCHASE ST | HANCOCK ST | 2026 | Poor | Mill & Overlay | 380.8515 | 0.072131 | 45 | 2025 | TBD | 77342.9706
LIME STREET | MILK ST | WATER ST | 2026 | Poor | Mill & Overlay/ Reclamation | 1180.74 | 0.27 | 50 | 2025 | TBD | 242886.2808
SHIP STREET | WATER ST | BECK ST | 2026 | Fair | Mill & Overlay | 570.5828 | 0.10806 | 71 | 2025 | TBD | 72865.4204
BECK STREET | SHIP ST | SMITH ST | 2026 | Poor | Reclamation | 105.216 | 0.019927 | 29 | 2025 | TBD | 24698.3473
| SMITH ST | LIME ST | 2026 | Poor | Reclamation | 198.4458 | 0.037584 | 39 | 2025 | TBD | 54408.7319
NEPTUNE STREET | PURCHASE ST | WATER ST | 2024 | Fair | Mill & Overlay | 635.1835 | 0.1203 | 72 | 2023 | TBD | 172342.4537
[8 empty] | TOTAL |  |  | 472201.7509

## WARD2
Ward 2 FY 24
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
FAIR ST | CHARTER ST | SPRING ST | 2023 | Very Poor | Reclamation | 138.9981 | 0.026325 | 28 | TBD | TBD | 12598.7899
| ESSEX ST | MIDDLE ST | 2023 | Poor | Reclamation | 172.9443 | 0.032755 | 49 | TBD | TBD | 15675.6754
| LIBERTY ST | WATER ST | 2023 | Fair | Reclamation | 530.6646 | 0.1005 | 61 | TBD | TBD | 74821.3492
| MIDDLE ST | LIBERTY ST | 2023 | Poor | Reclamation | 187.8804 | 0.035583 | 58 | TBD | TBD | 26490.3015
| ORANGE ST | CHARTER ST | 2023 | Very Poor | Reclamation | 63.4879 | 0.012024 | 23 | TBD | TBD | 5754.5394
| PROSPECT ST | TEMPLE ST | 2023 | Poor | Reclamation | 166.2964 | 0.031496 | 60 | TBD | TBD | 15073.1021
| SPRING ST | ESSEX ST | 2023 | Very Poor | Reclamation | 85.7168 | 0.016234 | 8 | TBD | TBD | 7769.3738
| TEMPLE ST | ORANGE ST | 2023 | Very Poor | Reclamation | 171.4936 | 0.03248 | 34 | TBD | TBD | 25727.1807
FRUIT ST | HIGH ST | PROSPECT ST | 2023 | Poor | Mill & Overlay | 576.4722 | 0.10918 | 59 | 2022 | Brick | 150834.2929
MIDDLE ST | CENTER ST | FAIR ST | 2023 | Poor | Reclamation | 338.995 | 0.064204 | 51 | TBD | TBD | 61193.1266
| FAIR ST | INDEPENDENT ST | 2023 | Very Poor | Reclamation | 193.4276 | 0.036634 | 29 | TBD | TBD | 47771.7595
| INDEPENDENT ST | FEDERAL ST | 2023 | Very Poor | Reclamation | 416.6596 | 0.078913 | 35 | TBD | TBD | 92232.8384
[8 empty] | TOTAL |  |  | 535942.3293
Ward 2 FY 26
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
ALLEN STREET | HIGH ST | PROSPECT ST | 2025 | Poor | Reclamation | 655.2628 | 0.1241 | 25 | 2024 | TBD | 284496.3619
SCHOOL STREET | FEDERAL ST | LIME ST | 2025 | Poor | Mill & Overlay | 602.8585 | 0.11418 | 59 | 2024 | TBD | 230221.799
GARDEN STREET | OTIS PL | STATE ST | 2025 | Poor | Mill & Overlay | 338.0507 | 0.064025 | 59 | 2024 | TBD | 128333.3816
INDEPENDENT STREET | WATER ST | MIDDLE ST | 2025 | Poor | Mill & Overlay | 602 | 0.12 | 60 | 2024 | TBD | 230221
[8 empty] | TOTAL |  |  | 873272.5424
Ward 2 FY 28
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
BROMFIELD COURT | BROMFIELD ST | DEAD END | 2027 | Very Poor | Reclamation | 322.3064 | 0.061043 | 27 | 2026 | Concrete | 32459.8344
BROMFIELD STREET | HIGH ST | WATER ST | 2027 | Poor | Mill & Overlay | 322.3064 | 0.061043 | 51 | 2026 | Concrete | 173186.42
ATWOOD STREET | LIME ST | FEDERAL ST | 2027 | Poor | Mill & Overlay | 597.7448 | 0.11321 | 56 | 2026 | Concrete | 30099.7699
BECK STREET | FEDERAL ST | LIME ST | 2027 | Very Poor | Reclamation | 296.544 | 0.056164 | 22 | 2026 | Brick | 29865.2724
CENTER STREET | LIBERTY ST | WATER ST | 2027 | Very Poor | Mill & Overlay | 427.3522 | 0.080938 | 40 | 2026 | Brick | 39367.6036
SPRING STREET | FAIR ST | FEDERAL ST | 2027 | Poor | Mill & Overlay | 609.205 | 0.11538 | 59 | 2026 | Concrete | 53744.5405
[8 empty] | TOTAL |  |  | 358723.4408

## WARD3
Ward 3 FY 23
Street Name | From Street | To Street | Road Repair Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
BOARDMAN ST | ATKINSON ST | MERRIMAC ST | 2022 - COMPLETE | Poor | Mill & Overlay | 559.1442 | 0.1059 | 54 | 2022 | Brick | 115000
| HIGH ST | WASHINGTON ST | 2022 - COMPLETE | Poor | Mill & Overlay | 441.8113 | 0.083676 | 48 | 2022 | Brick | 115000
| WASHINGTON ST | ATKINSON ST | 2022 - COMPLETE | Poor | Mill & Overlay | 345.4089 | 0.065418 | 48 | 2022 | Brick | 115000
BRICHER PLACE | HILL ST | QUILL ST | 2022 - COMPLETE | Poor | Mill & Overlay | 200.0579 | 0.03789 | 18 | TBD | TBD | 16500
BRICHER PLACE | QUILL ST | CHERRY ST | 2022 - COMPLETE | Poor | Mill & Overlay | 166.0715 | 0.031453 | 15 | TBD | TBD | 16500
CHERRY ST | ROUTE 1 | CHERRY ST EXT | 2022 - COMPLETE | Poor | Reclamation | 815.1388 | 0.15438 | 39 | TBD | TBD | 27500
| CHERRY ST EXT | BRICHER PL | 2022 - COMPLETE | Poor | Reclamation | 616.881 | 0.11683 | 53 | TBD | TBD | 27500
DEXTER LN | HIGH ST | DEAD END | 2022 - COMPLETE | Poor | Mill & Overlay | 843.0481 | 0.15967 | 52 | TBD | TBD | 36000
NEW PASTURE WY | GRAF RD | CUL DE SAC | 2022 - COMPLETE | Fair | Mill & Overlay | 1484.7155 | 0.2812 | 24 | TBD | TBD | 72000
QUILL ST | BRICHER PL | DEAD END | 2022 - COMPLETE | Poor | Mill & Overlay | 201.3886 | 0.038142 | 34 | TBD | TBD | 15000
STANLEY TUCKER DR | MALCOLM K. HOYT RD | CUL DE SAC | 2022 - COMPLETE | Poor | Mill & Overlay | 1019.6308 | 0.19311 | 43 | TBD | TBD | 61000
VERNON ST | CAREY AVE | DEAD END | 2022 - COMPLETE | Very Poor | Reclamation | 96.5283 | 0.018282 | 0 | TBD | TBD | 8000
[8 empty] | TOTAL |  |  | 625000
Ward 3 FY 25
Street Name | From Street | To Street | Road Repair Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
JOHNSON STREET | LOW ST | HIGH ST | 2024 | Poor | Mill & Overlay | 1686.1412 | 0.31934 | 42 | 2024 | TBD | 458931.1076
CALDWELLS COURT | MERRIMAC ST | DEAD END | 2024 | Poor | Mill & Overlay | 147.0713 | 0.027854 | 32 | 2024 | TBD | 6665.2699
BIRCH STREET | MARKET ST | SUMMER ST | 2024 | Poor | Mill & Overlay | 179.2788 | 0.033954 | 40 | 2024 | TBD | 8124.9148
CURRIERS COURT | KENT ST | DEAD END | 2024 | Fair | Mill & Overlay | 152.6814 | 0.028917 | 75 | 2024 | TBD | 4613.015
PAPANTI COURT | OCEAN ST | DEAD END | 2024 | Fair | Mill & Overlay | 167.6134 | 0.031745 | 79 | 2024 | TBD | 6752.2136
EAGLE STREET | KENT ST | WARREN ST | 2026 | Poor | Mill & Overlay | 487.1602 | 0.092265 | 45 | 2026 | TBD | 146575.7803
| WARREN ST | CARTER ST | 2026 | Poor | Mill & Overlay | 271.401 | 0.051402 | 39 | 2026 | TBD | 31925.605
[8 empty] | TOTAL |  |  | 663587.9062
Ward 3 FY 27
Street Name | From Street | To Street | Road Repair Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
SUMMIT PLACE | TOPPAN'S LN | HIGH ST | 2026 | Poor | Mill & Overlay | 1709.0958 | 0.32369 | 51 | 2026 | TBD | 387050.4971
PREBLE ROAD | PERKINS WY | SPLIT | 2026 | Fair | Mill & Overlay | 456.1854 | 0.086399 | 70 | 2026 | TBD | 27565.7627
| SPLIT | CUL DE SAC | 2026 | Poor | Mill & Overlay | 496.1532 | 0.093968 | 42 | 2026 | TBD | 29980.8823
COTTAGE COURT | POND ST | DEAD END | 2026 | Poor | Reclamation | 478.2471 | 0.090577 | 30 | 2026 | TBD | 43348.3176
PERKINS WAY | PARKER ST | PREBLE RD | 2024 | Fair | Mill & Overlay | 962.7786 | 0.18234 | 69 | 2024 | TBD | 72721.8785
| PREBLE RD | CUL DE SAC | 2024 | Fair | Mill & Overlay | 306.6024 | 0.058069 | 74 | 2024 | TBD | 23158.6984
[8 empty] | TOTAL |  |  | 583826.0367

## WARD4
Ward 4 FY 24
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
ARLINGTON ST | HIGHLAND AVE | HIGH ST | 2023 | Very Poor | Reclamation (Binder Only) | 907.4868 | 0.17187 | 28 | 2024 | Concrete | 492018.1002
CHRISTOPHER ST | PLUMMER AVE | JEFFERSON ST | 2023 | Very Poor | Reclamation | 673.3218 | 0.12752 | 36 | NA | NA | 88154.2783
WILLOW AVE | HIGH ST | MAPLE ST | 2023 | Very Poor | Reclamation | 566.3028 | 0.10725 | 12 | 2023 | Asphalt | 40000
PLUMMER AVE | HIGH ST | MERRIMAC ST | 2023 | Very Poor | Reclamation | 1543 | 0.29 | 22 | 2023 | Concrete | 125000
[8 empty] | TOTAL |  |  | 745172.3785
Ward 4 FY 26
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
ADAMS STREET | JEFFERSON ST | UPLAND RD | 2025 | Poor | Mill & Overlay | 411.0467 | 0.07785 | 45 | 2024 | TBD | 82187.6449
ADAMS STREET | UPLAND RD | DEAD END | 2025 | Poor | Reclamation | 114.3347 | 0.021654 | 16 | 2024 | TBD | 38491.8168
ASHLAND COURT | ASHLAND ST | DEAD END | 2025 | Poor | Mill & Overlay | 344.9192 | 0.065326 | 51 | 2024 | TBD | 20842.3148
BUTLER STREET | MERRIMAC ST | HOWARD ST | 2025 | Poor | Mill & Overlay | 486.811 | 0.092199 | 42 | 2024 | TBD | 90383.6194
CALIFORNIA STREET |  | WALNUT ST | 2025 | Poor | Mill & Overlay | 323.1551 | 0.061204 | 43 | 2024 | TBD | 95727.8952
DAWES STREET | COOLIDGE ST | ASHLAND ST | 2025 | Poor | Mill & Overlay | 564.1543 | 0.10685 | 58 | 2024 | TBD | 42341.1241
FARRELL STREET | RAWSON AVE | MCCLINTOCK AVE | 2025 | Poor | Mill & Overlay | 597.7972 | 0.11322 | 57 | 2024 | TBD | 214518.1013
FARRELL STREET | MCCLINTOCK AVE | COLUMBUS AVE | 2025 | Poor | Mill & Overlay | 252.0142 | 0.04773 | 57 | 2024 | TBD | 47545.1785
MUNROE STREET | KENT ST | OAKLAND ST | 2025 | Poor | Mill & Overlay | 1568.4 | 0.297 | 55 | TBD | TBD | 75000
[8 empty] | TOTAL |  |  | 632037.6949
Ward 4 FY 28
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
ASHLAND COURT | ASHLAND ST | DEAD END | 2027 | Poor | Mill & Overlay | 344.9192 | 0.065326 | 48 | NA | NA | 20842.3146
ASHLAND STREET | HIGH ST | MERRIMAC ST | 2027 | Very Poor | Reclamation | 1310.3986 | 0.24818 | 24 | 2026 | Concrete | 237549.0626
DAWES STREET | ASHLAND ST | COOLIDGE ST | 2027 | Poor | Mill & Overlay | 564.1543 | 0.10685 | 55 | 2026 | Concrete | 28408.304
COOLIDGE STREET | ASHLAND ST | PARKER RIDGE WAY EAST | 2027 | Poor | Mill & Overlay | 286.5226 | 0.054266 | 42 | 2026 | Concrete | 13706.6057
TYNG STREET | MERRIMAC ST | MUNROE ST | 2027 | Very Poor | Reclamation | 898.425 | 0.17016 | 31 | 2026 | Concrete | 217155.3141
[8 empty] | TOTAL |  |  | 517661.601

## WARD5
Ward 5 FY 23
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
HIGHLAWN TER | HIGH ST | DEAD END | 2022- COMPLETE | Poor | Mill & Overlay | 280.757 | 0.053174 | 46 | TBD | TBD | 5000
HOPE AVE | ALBERTA AVE | IONA AVE | 2022- COMPLETE | Very Poor | Reclamation | 505.73 | 0.095782 | 37 | TBD | TBD | 33000
QUAIL RUN HOLLOW | DOE RUN DR | FOX RUN RD | 2022- COMPLETE | Poor | Mill & Overlay | 379.5895 | 0.071892 | 49 | TBD | TBD | 23333.3333
| FOX RUN RD | PHEASANT RUN DR | 2022- COMPLETE | Poor | Mill & Overlay | 374.5544 | 0.070938 | 49 | TBD | TBD | 23333.3333
| PHEASANT RUN DR | WILDWOOD DR | 2022- COMPLETE | Poor | Mill & Overlay | 272.0334 | 0.051521 | 52 | TBD | TBD | 23333.3333
FOX RUN DRIVE | SQUIRES GLEN | DRIVEWAY #11 | 2022- COMPLETE | Fair | Mill & Overlay | 583.9783 | 0.1106 | 60 | TBD | TBD | 42000
| DRIVEWAY #11 | QUAIL RUN HOLLOW | 2022- COMPLETE | Poor | Mill & Overlay | 587.845 | 0.11133 | 56 | TBD | TBD | 35000
SIMMONS DRIVE | NORTH ATKINSON ST | GOLDEN DR | 2022- COMPLETE | Fair | Mill & Overlay | 258.37 | 0.048934 | 66 | TBD | TBD | 12333.3333
| GOLDEN DR | GOLDEN DR | 2022- COMPLETE | Fair | Mill & Overlay | 245.26 | 0.046451 | 66 | TBD | TBD | 12333.3333
| GOLDEN DR | DEAD END | 2022- COMPLETE | Poor | Mill & Overlay | 228.0764 | 0.043196 | 59 | TBD | TBD | 12333.3333
STICKNEY AVENUE | ALBERTA AVE | LOW ST | 2022- COMPLETE | Fair | Mill & Overlay | 549.7361 | 0.10412 | 70 | TBD | TBD | 26000
DOE RUN DRIVE | HALE ST | CUL DE SAC | 2022- COMPLETE | Poor | Mill & Overlay | 1200 | 0.23 | 63 | TBD | TBD | 79000
PHEASANT RUN DR | QUAIL RUN | SQUIRE GLEN | 2022- COMPLETE | Fair | Mill & Overlay | 1825.6086 | 0.34576 | 70 | TBD | TBD | 85000
[8 empty] | TOTAL |  |  | 412000
Ward 5 FY 25
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
ALBERTA AVENUE | WILLIAMSON AVE | DEAD END | 2024 | Poor | Mill & Overlay | 66.75 | 0.012642 | 56 | 2023 | TBD | 4033.4789
| WILLIAMSON AVE | STICKNEY AVE | 2024 | Poor | Mill & Overlay | 253.4558 | 0.048003 | 58 | 2023 | TBD | 15315.4878
| STICKNEY AVE | HOPE AVE | 2024 | Poor | Mill & Overlay | 133.5659 | 0.025297 | 59 | 2023 | TBD | 8070.9412
| HOPE AVE | BRISSETTE AVE | 2024 | Poor | Mill & Overlay | 107.292 | 0.02032 | 54 | 2023 | TBD | 6483.2958
| BRISSETTE AVE | MYRTLE AVE | 2024 | Fair | Mill & Overlay | 132.1053 | 0.02502 | 69 | 2023 | TBD | 7982.6824
| MYRTLE AVE | AVON ST | 2024 | Poor | Mill & Overlay | 119.0462 | 0.022547 | 56 | 2023 | TBD | 7193.5664
| AVON ST | END | 2024 | Poor | Reclamation | 75.4481 | 0.014289 | 34 | 2023 | TBD | 9118.1528
BOWLEN AVENUE | IONA AVE | MYRTLE AVE | 2024 | Poor | Mill & Overlay | 689.2836 | 0.13055 | 56 | 2023 | TBD | 41651.1126
CHARMANSKI DRIVE | WILDWOOD DR | DEAD END | 2024 | Poor | Mill & Overlay | 256.0165 | 0.048488 | 60 | 2023 | TBD | 58489.5967
CHARRON DRIVE | NORTH ATKINSON ST | CUL DE SAC | 2024 | Poor | Reclamation | 726.9973 | 0.13769 | 20 | 2023 | TBD | 80538.3785
CROW LANE | TURKEY HILL RD | VIRGINIA LN | 2024 | Poor | Mill & Overlay | 1294.6322 | 0.2452 | 60 | 2023 | TBD | 78230.3114
RAWSON AVENUE | HIGH ST | LOIS ST | 2024 | Poor | Mill & Overlay | 1629.04 | 0.28 | 60 | 2023 | TBD | 90000
[8 empty] | TOTAL |  |  | 317107.0043
Ward 5 FY 27
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
GOLDSMITHS DRIVE | LAVALEE LN | BRADBURY LN | 2026 | Poor | Mill & Overlay | 317.291 | 0.060093 | 59 | 2025 | TBD | 63755.9857
| BRADBURY LN | ANDERSON LN | 2026 | Fair | Mill & Overlay | 314.3875 | 0.059543 | 65 | 2025 | TBD | 97623.3776
| ANDERSON LN | FRANCES DR | 2026 | Poor | Mill & Overlay | 923.4952 | 0.1749 | 56 | 2025 | TBD | 248425.9655
| FRANCES DR | DEAD END | 2026 | Poor | Mill & Overlay | 276.7663 | 0.052418 | 15 | 2025 | TBD | 52047.3528
NORTH ATKINSON STREET | CHARRON DR | SIMMONS DR | 2026 | Poor | Mill & Overlay | 448.811 | 0.085002 | 43 | 2025 | TBD | 117858.3869
| SIMMONS DR | LOW ST | 2026 | Fair | Mill & Overlay | 314.6148 | 0.059586 | 64 | 2025 | TBD | 35645.8587
IONA AVENUE | HOPE AVE | BOWLEN AVE | 2026 | Poor | Mill & Overlay | 123.694 | 0.023427 | 58 | 2025 | TBD | 6228.6822
| BOWLEN AVE | MYRTLE AVE | 2026 | Poor | Mill & Overlay | 123.7553 | 0.023439 | 52 | 2025 | TBD | 6231.7686
NORMAN AVENUE | NORTH ATKINSON ST | MURPHY AVE | 2026 | Poor | Mill & Overlay | 796.446 | 0.15084 | 56 | 2025 | TBD | 90000
[8 empty] | TOTAL |  |  | 717817.3779

## WARD6
Ward 6 FY 24
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
NOBLE STREET | COOMBS CIR | STOREY AVE | 2023 | Very Poor | Reclamation | 1358.7739 | 0.25734 | 20 | NA | NA | 164212.3531
PETERS ROAD | MARQUAND RD | HAWTHORNE RD | 2023 | Poor | Mill & Overlay | 497.6328 | 0.094249 | 55 | NA | NA | 30070.2922
HOYTS LN | STOREY AVE | CURZON'S MILL RD | 2023 | Poor | Mill & Overlay | 1856.4067 | 0.35159 | 61 | NA | NA | 194282.6453
SPRING LN | FERRY RD | DEAD END | 2023 | Very Poor | Reclamation | 1783.7075 | 0.33782 | 8 | NA | NA | 114157.2818
LONGFELLOW DRIVE | TURKEY HILL RD | 28 LONGFELLOW DRIVE | 2023 | Poor | Mill & Overlay | 1077.3279 | 0.20404 | 58 | NA | NA | 92000
CURZON'S MILL RD | HOYTS LN | DEAD END | 2023 | Very Poor | Reclamation | 3071.6137 | 0.58175 | 33 | NA | NA | 262111.0379
[8 empty] | TOTAL |  |  | 856833.6103
Ward 6 FY 26
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
PHILIPS DRIVE | STOREY AVE | STOREY AVE | 2025 | Very Poor | Reclamation | 3134.454 | 0.59365 | 34 | 2024 | Asphalt | 398230.5135
DREW STREET | HOYTS LN | PHILIPS DR | 2025 | Poor | Mill & Overlay | 1411.3412 | 0.2673 | 53 | 2024 | Asphalt | 63301.9035
RYAN ROAD | PHILIPS DR | PHILIPS DR | 2025 | Very Poor | Reclamation | 444.0475 | 0.0841 | 36 | 2024 | Asphalt | 62608.7214
SULLIVAN DRIVE | PHILIPS DR | PHILIPS DR | 2025 | Very Poor | Reclamation | 889.343 | 0.16844 | 36 | 2024 | Asphalt | 107480.0636
BRIGGS AVENUE | FERRY RD | FENDERS AVE | 2025 | Poor | Mill & Overlay | 367.0188 | 0.069511 | 54 | 2024 | TBD | 22177.72
| FENDERS AVE | BROWN AVE | 2025 | Poor | Mill & Overlay | 268.8894 | 0.050926 | 54 | 2024 | TBD | 16248.0889
| BROWN AVE | CUL DE SAC | 2025 | Fair | Mill & Overlay | 216.5075 | 0.041005 | 62 | 2024 | TBD | 11993.8998
[8 empty] | TOTAL |  |  | 682040.9107
Ward 6 FY 28
Street Name | From Street | To Street | Road Repair Calendar Year | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Sidewalk Repair Calendar Year | Sidewalk Material Proposed | Estimated Cost
BOURBEAU TER | TURKEY HILL RD | TURKEY HILL RD | 2025 | Poor | Mill & Overlay | 1994.6707 | 0.37778 | 44 | 2024 | Asphalt | 413568.7791
MOSELEY AVENUE | ERIE AVE | HARDING AVE | 2025 | Poor | Mill & Overlay | 314.0425 | 0.059478 | 52 | 2024 | TBD | 69329.7373
| HARDING AVE | ELMIRA AVE | 2025 | Poor | Mill & Overlay | 264.7276 | 0.050138 | 57 | 2024 | TBD | 42700.1824
DENNETT DRIVE | EVERETTE DRIVE | FINNEGAN WY | 2027 | Poor | Mill & Overlay | 953.526 | 0.18059 | 47 | NA | NA | 54342.1637
EVERETTE DRIVE | TURKEY HILL RD | CUL DE SAC | 2027 | Very Poor | Reclamation | 1119.31 | 0.21 | 32 | NA | NA | 135272.43
[8 empty] | TOTAL |  |  | 715213.2926

## Sidewalks 2022 (hidden)
Ward | Street Name | From Street | To Street | Length (Ft) | Length (Mi) | Road Surface Rating (RSR) | Road Condition | Sidewalk + Curb Calendar Year | Road Calendar Year | Proposed Curb Mat'l | Current Sidewalk Mat'l | Current Sidewalk replacement Cost (FY22) | Proposed sidewalk material | Proposed Sidewalk Cost (FY22) | Planned Sidewalk Spending (FY22) | Funding Source
1 | ALTER COURT | BARTON ST | DEAD END | 179.2454 | 0.033948 | 29 | Poor | NA | 2022 | Granite | Concrete | 8800 | Asphalt | 9000 | 0 | ARPA
1 | BARTON COURT | BARTON ST | DEAD END | 203.9173 | 0.038621 | 10 | Poor | NA | 2022 | Granite | None | 16600 | Asphalt | 9000 | 0 | ARPA
1 | BARTON STREET | ALTER CT | BARTON CT | 250.804 | 0.047501 | 6 | Poor | 2022 | 2022 | Granite | Concrete | 16600 | Asphalt | 9000 | 0 | ARPA
1 | BARTON STREET | BARTON CT | CHESTNUT ST | 260.7549 | 0.049385 | 6 | Poor | 2022 | 2022 | Granite | Concrete | 16600 | Asphalt | 9000 | 0 | ARPA
1 | BARTON STREET | HIGH ST | ALTER CT | 395.9725 | 0.074995 | 20 | Poor | 2022 | 2022 | Granite | Concrete | 16600 | Asphalt | 9000 | 0 | ARPA
2 | FRUIT ST | HIGH ST | PROSPECT ST | 576.4722 | 0.10918 | 59 | Poor | 2022 | 2023 | Granite | Brick | 116000 | Brick | 116000 | 116000 | CP 90
2 | MIDDLE ST | CENTER ST | FAIR ST | 338.995 | 0.064204 | 51 | Poor | 2022 | 2023 | Granite | Brick | 69000 | Brick | 69000 | 0 | Meals
2 | FAIR ST | CHARTER ST | SPRING ST | 138.9981 | 0.026325 | 28 | Very Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | ESSEX ST | MIDDLE ST | 172.9443 | 0.032755 | 49 | Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | LIBERTY ST | WATER ST | 530.6646 | 0.1005 | 61 | Fair | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | MIDDLE ST | LIBERTY ST | 187.8804 | 0.035583 | 58 | Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | ORANGE ST | CHARTER ST | 63.4879 | 0.012024 | 23 | Very Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | PROSPECT ST | TEMPLE ST | 166.2964 | 0.031496 | 60 | Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | SPRING ST | ESSEX ST | 85.7168 | 0.016234 | 8 | Very Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | FAIR ST | TEMPLE ST | ORANGE ST | 171.4936 | 0.03248 | 34 | Very Poor | 2022 | 2023 | Granite | Brick | 40625 | Brick and Concrete | 29281.25 | 0 | CP 90
2 | MIDDLE ST | FAIR ST | INDEPENDENT ST | 193.4276 | 0.036634 | 29 | Very Poor | 2022 | 2023 | Granite | Brick | 69000 | Concrete | 39333.3333 | 0 | Meals
2 | MIDDLE ST | INDEPENDENT ST | FEDERAL ST | 416.6596 | 0.078913 | 35 | Very Poor | 2022 | 2023 | Granite | Brick | 69000 | Concrete | 39333.3333 | 0 | Meals
2 | MILK ST | FEDERAL ST | LIME ST | 612.1002 | 0.11593 | 59 | Poor | 2022 | 2023 | Granite | Brick | 145500 | Concrete | 64000 | 0 | Meals
2 | MILK ST | LIME ST | FRANKLIN ST | 501.8944 | 0.095056 | 37 | Very Poor | 2022 | 2023 | Granite | Brick | 145500 | Concrete | 64000 | 0 | Meals
3 | BOARDMAN ST | ATKINSON ST | MERRIMAC ST | 559.1442 | 0.1059 | 54 | Poor | 2022 | 2022 | Granite | Brick | 110000 | Brick | 110000 | 110000 | CP 90
3 | BOARDMAN ST | HIGH ST | WASHINGTON ST | 441.8113 | 0.083676 | 48 | Poor | 2022 | 2022 | Granite | Brick | 110000 | Brick | 110000 | 110000 | CP 90
3 | BOARDMAN ST | WASHINGTON ST | ATKINSON ST | 345.4089 | 0.065418 | 48 | Poor | 2022 | 2022 | Granite | Brick | 110000 | Brick | 110000 | 110000 | CP 90
4 | ARLINGTON ST | HIGHLAND AVE | HIGH ST | 907.4868 | 0.17187 | 28 | Very Poor | 2022 | 2023 | Granite | Brick | 658000 | Concrete | 207000 | 207000 | Meals
6 | BOURBEAU TER | TURKEY HILL RD | TURKEY HILL RD | 1994.6707 | 0.37778 | 44 | Poor | 2022 | 2023 | Asphalt | Asphalt | 52000 | Asphalt | 52000 | 52000 | Meals
[13 empty] | TOTAL | 1259916.6667 | 705000

## Surface treatment
Street Name | From Street | To Street | Year | Funding Source | General Condition | Proposed Repair Method | Length (Ft) | Length (Miles) | Road Surface Rating (RSR) | Estimated Total Cost (Includes Sidewalk Replace in Kind Cost Estimate)
OLD POINT ROAD | FLORA ST | G ST | 2026 | $2M Budget | Fair | Surface Treatment | 139.0262 | 0.026331 | 65 | 3500.372
| G ST | H ST | 2026 | $2M Budget | Good | Surface Treatment | 162.0214 | 0.030686 | 70 | 4079.3381
| H ST | IRIS ST | 2026 | $2M Budget | Fair | Surface Treatment | 152.9963 | 0.028977 | 63 | 3852.1057
| IRIS ST | K ST | 2026 | $2M Budget | Good | Surface Treatment | 281.9804 | 0.053405 | 68 | 7099.6403
| K ST | L ST | 2026 | $2M Budget | Fair | Surface Treatment | 142.0652 | 0.026906 | 63 | 3576.8858
| L ST | M ST | 2026 | $2M Budget | Good | Surface Treatment | 147.9386 | 0.028019 | 71 | 3724.7656
| M ST | N ST | 2026 | $2M Budget | Fair | Surface Treatment | 148.6998 | 0.028163 | 63 | 3743.9312
| N ST | O ST | 2026 | $2M Budget | Good | Surface Treatment | 144.2599 | 0.027322 | 69 | 3632.1428
| O ST | P ST | 2026 | $2M Budget | Good | Surface Treatment | 101.0728 | 0.019143 | 73 | 2544.7896
OVERLOOK STREET | 64TH ST | 66TH ST | 2026 | $2M Budget | Good | Surface Treatment | 576.7428 | 0.10923 | 75 | 7260.551
| 76TH ST | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 177.0003 | 0.033523 | 80 | 2228.2369
P STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 276.7073 | 0.052407 | 67 | 4180.1251
RESERVATION TERRACE | 57TH ST | 55TH ST | 2026 | $2M Budget | Fair | Surface Treatment | 162.2318 | 0.030726 | 67 | 2450.7819
| 61ST ST | GRANT ST | 2026 | $2M Budget | Good | Surface Treatment | 70.526 | 0.013357 | 84 | 1065.4134
| 63RD ST | 61ST ST | 2026 | $2M Budget | Good | Surface Treatment | 152.0274 | 0.028793 | 81 | 2296.6277
| 67TH ST | 63RD ST | 2026 | $2M Budget | Good | Surface Treatment | 310.5167 | 0.05881 | 80 | 4690.8727
| 69TH ST | 67TH ST | 2026 | $2M Budget | Good | Surface Treatment | 160.1804 | 0.030337 | 81 | 2419.7916
| 73RD ST | 69TH ST | 2026 | $2M Budget | Good | Surface Treatment | 323.3468 | 0.06124 | 79 | 4884.6917
| 77TH ST | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 843.282 | 0.15971 | 65 | 12739.1801
| GRANT ST | 57TH ST | 2026 | $2M Budget | Good | Surface Treatment | 248.2341 | 0.047014 | 78 | 3749.9903
SHORE DRIVE | 56TH ST | 58TH ST | 2026 | $2M Budget | Good | Surface Treatment | 152.0794 | 0.028803 | 73 | 2297.4135
| 58TH ST | 60TH ST | 2026 | $2M Budget | Good | Surface Treatment | 173.0365 | 0.032772 | 82 | 2614.0046
| 60TH ST | 62ND ST | 2026 | $2M Budget | Good | Surface Treatment | 157.3458 | 0.0298 | 84 | 2376.9712
| 62ND ST | 64TH ST | 2026 | $2M Budget | Good | Surface Treatment | 163.9658 | 0.031054 | 82 | 2476.9766
| 64TH ST | 76TH ST | 2026 | $2M Budget | Fair | Surface Treatment | 872.1444 | 0.16518 | 60 | 13175.1946
NORTHERN BLVD | 76TH ST | 73RD ST | 2025 | $2M Budget | Fair | Surface Treatment | 93.0259 | 0.017619 | 68 | 2576.404
NORTHERN BLVD | 77TH ST | 76TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 133.0178 | 0.025193 | 68 | 3684.0008
NORTHERN BLVD | 78TH ST | 77TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 607.2427 | 0.11501 | 68 | 16817.9251
NORTHERN BLVD | 80TH ST | 78TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 468.6678 | 0.088763 | 73 | 12980.0163
NORTHERN BLVD | 82NDST | 80TH ST | 2025 | $2M Budget | Good | Surface Treatment | 201.988 | 0.038255 | 81 | 5594.1694
NANCY STREET | OLD POINT RD | END | 2026 | $2M Budget | Fair | Surface Treatment | 198.6765 | 0.037628 | 67 | 3501.5629
NORTHERN BLVD | 53RD ST | 56TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 50.7315 | 0.0096082 | 68 | 1405.0371
NORTHERN BLVD | 55TH ST | 58TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 66.8365 | 0.012658 | 68 | 1851.0737
NORTHERN BLVD | 56TH ST | NEWBURY TL | 2025 | $2M Budget | Fair | Surface Treatment | 102.1818 | 0.019353 | 68 | 2829.9825
NORTHERN BLVD | 57TH ST | 60TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 50.9805 | 0.0096554 | 68 | 1411.9331
NORTHERN BLVD | 58TH ST | 53RD ST | 2025 | $2M Budget | Fair | Surface Treatment | 90.6733 | 0.017173 | 68 | 2511.2466
NORTHERN BLVD | 59TH ST | 62ND ST | 2025 | $2M Budget | Fair | Surface Treatment | 44.0357 | 0.0083401 | 68 | 1219.5943
NORTHERN BLVD | 60TH ST | 55TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 109.4401 | 0.020727 | 68 | 3031.0046
NORTHERN BLVD | 61ST ST | 59TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 141.1286 | 0.026729 | 70 | 3908.6337
NORTHERN BLVD | 62ND ST | 57TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 101.5906 | 0.019241 | 68 | 2813.6086
NORTHERN BLVD | 65TH ST | 63RD ST | 2025 | $2M Budget | Fair | Surface Treatment | 137.6377 | 0.026068 | 68 | 3811.9512
NORTHERN BLVD | 66TH ST | 61ST ST | 2025 | $2M Budget | Fair | Surface Treatment | 170.0058 | 0.032198 | 68 | 4708.4058
NORTHERN BLVD | 67TH ST | 65TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 161.0109 | 0.030494 | 68 | 4459.2856
NORTHERN BLVD | 69TH ST | 70TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 54.7232 | 0.010364 | 68 | 1515.59
NORTHERN BLVD | 70TH ST | 67TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 82.8805 | 0.015697 | 68 | 2295.4206
NORTHERN BLVD | 71ST ST | 72ND ST | 2025 | $2M Budget | Fair | Surface Treatment | 54.9347 | 0.010404 | 68 | 1521.4481
NORTHERN BLVD | 72ND ST | 69TH ST | 2025 | $2M Budget | Fair | Surface Treatment | 104.1876 | 0.019732 | 68 | 2885.5326
L ST | OLD POINT RD | DEAD END | 2025 | $2M Budget | Fair | Surface Treatment | 440.5292 | 0.083434 | 67 | 5545.7727
LOUISA STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 171.5933 | 0.032499 | 63 | 2160.1686
M ST | OLD POINT RD | DEAD END | 2025 | $2M Budget | Fair | Surface Treatment | 326.2306 | 0.061786 | 68 | 4928.2571
MARTHA STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 136.6174 | 0.025875 | 83 | 1719.8612
H STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 386.0593 | 0.073117 | 75 | 5832.0686
HARBOR STREET | 78TH ST | 80TH ST | 2026 | $2M Budget | Good | Surface Treatment | 438.8603 | 0.083117 | 81 | 7734.6692
HELENA STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 161.5951 | 0.030605 | 81 | 2034.3024
HIGH ST E | BROMFIELD ST | BARTON ST | 2024 | $2M Budget | Poor | Surface Treatment | 308.3574 | 0.058401 | 52 | 18633.0115
I STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 356.8367 | 0.067583 | 79 | 5390.6127
IRIS STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 250.6278 | 0.047467 | 60 | 3786.1506
JULIA STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 305.4357 | 0.057848 | 62 | 3845.0957
K ST | OLD POINT RD | DEAD END | 2025 | $2M Budget | Fair | Surface Treatment | 734.6082 | 0.13913 | 70 | 9247.9006
F STREET | HIGH ST | DEAD END | 2026 | $2M Budget | Poor | Mill & Overlay | 121.3015 | 0.022974 | 48 | 3054.1011
FLORA ST | OLD POINT RD | DEAD END | 2023 | $2M Budget | Fair | Surface Treatment | 347.2676 | 0.06577 | 72 | 4371.7131
G STREET | OLD POINT RD | DEAD END | 2026 | $2M Budget | Good | Surface Treatment | 223.7756 | 0.042382 | 78 | 3943.9213
GLORIA ST | OLD POINT RD | DEAD END | 2023 | $2M Budget | Fair | Surface Treatment | 437.9799 | 0.082951 | 66 | 5513.6802
74TH STREET | NORTHEN BLVD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 148.2264 | 0.028073 | 63 | 1866.0052
75TH STREET | NORTHERN BLVD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 327.9523 | 0.062112 | 62 | 6605.6876
76TH STREET | BARKER ST | OVERLOOK ST | 2026 | $2M Budget | Fair | Surface Treatment | 143.2352 | 0.027128 | 63 | 3606.344
| NORTHERN BLVD | BARKER ST | 2026 | $2M Budget | Fair | Surface Treatment | 185.8299 | 0.035195 | 63 | 4678.7838
| OVERLOOK ST | BASIN ST | 2026 | $2M Budget | Good | Surface Treatment | 105.4879 | 0.019979 | 75 | 2655.9503
77TH STREET | NORTHERN BLVD | RESERVATION TER | 2026 | $2M Budget | Fair | Surface Treatment | 258.2034 | 0.048902 | 63 | 3900.5927
78TH STREET | NORTHERN BLVD | HARBOR ST | 2026 | $2M Budget | Fair | Surface Treatment | 283.8682 | 0.053763 | 60 | 3573.5846
69TH STREET | NORTHERN BLVD | RESERVATION TER | 2026 | $2M Budget | Fair | Surface Treatment | 437.7787 | 0.082913 | 62 | 6613.3764
70TH STREET | NORTHEN BLVD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 313.2 | 0.059318 | 63 | 4731.4083
71ST STREET | NORTHERN BLVD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 261.309 | 0.04949 | 63 | 3947.508
72ND STREET | NORTHERN BLVD | DEAD END | 2026 | $2M Budget | Fair | Surface Treatment | 217.8537 | 0.04126 | 66 | 2742.5358
66TH STREET | NORTHERN BLVD | OVERLOOK ST | 2026 | $2M Budget | Fair | Surface Treatment | 269.7439 | 0.051088 | 60 | 3395.7763
67TH STREET | NORTHERN BLVD | RESERVATION TER | 2026 | $2M Budget | Fair | Surface Treatment | 466.2444 | 0.088304 | 63 | 7043.3983
64TH STREET | NORTHERN BLVD | OVERLOOK ST | 2026 | $2M Budget | Fair | Surface Treatment | 373.0343 | 0.07065 | 60 | 5635.3047
64TH STREET | OVERLOOK ST | SHORE DR | 2026 | $2M Budget | Fair | Surface Treatment | 96.5058 | 0.018278 | 63 | 1457.8805
64TH STREET | SHORE DR | SHORE DR | 2026 | $2M Budget | Good | Surface Treatment | 80.2892 | 0.015206 | 80 | 1212.9018
62ND STREET | SHORE DR | NORTHERN BLVD | 2026 | $2M Budget | Fair | Surface Treatment | 482.9115 | 0.091461 | 60 | 7295.1833
58TH STREET | NORTHERN BLVD | SHORE DR | 2026 | $2M Budget | Fair | Surface Treatment | 500.5742 | 0.094806 | 62 | 6301.6736
HIGH ST E | ALLEN ST | BROMFIELD ST | 2024 | $2M Budget | Fair | Surface Treatment | 280.2998 | 0.053087 | 66 | 16937.5828
| BARTON ST | MARLBORO ST | 2024 | $2M Budget | Fair | Surface Treatment | 251.1696 | 0.04757 | 63 | 15177.339
| EPPA WY | POND ST | 2024 | $2M Budget | Fair | Surface Treatment | 180.5124 | 0.034188 | 67 | 8180.8198
| FEDERAL ST | LIME ST | 2024 | $2M Budget | Poor | Surface Treatment | 610.727 | 0.11567 | 60 | 36904.1972
| FRUIT ST | TREMONT ST | 2024 | $2M Budget | Poor | Surface Treatment | 359.923 | 0.068167 | 47 | 21748.9479
| LIME ST | PARSONS ST | 2024 | $2M Budget | Fair | Surface Treatment | 311.915 | 0.059075 | 65 | 18847.9832
| PARK ST | EPPA WY | 2024 | $2M Budget | Fair | Surface Treatment | 67.9112 | 0.012862 | 80 | 3077.7367
| PARSONS ST | ALLEN ST | 2024 | $2M Budget | Fair | Surface Treatment | 240.8144 | 0.045609 | 64 | 14551.6085
| POND ST | STATE ST | 2024 | $2M Budget | Fair | Surface Treatment | 171.3509 | 0.032453 | 63 | 7765.621
| STATE ST | FRUIT ST | 2024 | $2M Budget | Poor | Surface Treatment | 503.6679 | 0.095392 | 58 | 30434.9731
| TREMONT ST | FEDERAL ST | 2024 | $2M Budget | Fair | Surface Treatment | 395.9865 | 0.074997 | 63 | 23928.1416
HIGH ST E | AUBURN ST | COURT ST | 2024 | $2M Budget | Fair | Surface Treatment | 228.3071 | 0.04324 | 63 | 10346.8796
| COURT ST | GREEN ST | 2024 | $2M Budget | Fair | Surface Treatment | 352.1881 | 0.066702 | 69 | 15961.1638
| GREEN ST | PARK ST | 2024 | $2M Budget | Fair | Surface Treatment | 278.0883 | 0.052668 | 63 | 12602.963
| MARKET ST | AUBURN ST | 2024 | $2M Budget | Fair | Surface Treatment | 105.5314 | 0.019987 | 65 | 4782.6813
| SUMMER ST | MARKET ST | 2024 | $2M Budget | Fair | Surface Treatment | 228.2018 | 0.04322 | 70 | 10342.107
ELM ST | PLUM ST | MERRIMAC ST | 2024 | $2M Budget | Fair | Surface Treatment | 379.4034 | 0.071857 | 63 | 48041.9492
GRIFFINS CT | WARREN ST | CARTER ST | 2024 | $2M Budget | Fair | Surface Treatment | 218.505 | 0.041384 | 58 | 3851.0284
DALTON ST | HILL ST | GREEN LEAF | 2023 | $2M Budget | Fair | Surface Treatment | 450.8749 | 0.085393 | 71 | 17028.0423
PAYSON ST | BEACON ST | WOODLAND ST | 2024 | $2M Budget | Fair | Surface Treatment | 403.8477 | 0.076486 | 53 | 79328.6393
| CHAPEL ST | BEACON ST | 2024 | $2M Budget | Fair | Surface Treatment | 241.2314 | 0.045688 | 55 | 65693.3288
MYRTLE AVENUE | BOWLEN AVE | IONA AVE | 2026 | $2M Budget | Fair | Surface Treatment | 455.8541 | 0.086336 | 70 | 13772.8718
| HIGH ST | BOWLEN AVE | 2026 | $2M Budget | Fair | Surface Treatment | 706.0515 | 0.13372 | 70 | 82317.3949
| IONA AVE | ALBERTA AVE | 2026 | $2M Budget | Fair | Surface Treatment | 461.5477 | 0.087414 | 72 | 13944.8938
COFFIN ST | MERRIMAC ST | DEAD END | 2023 | $2M Budget | Fair | Surface Treatment | 367.5284 | 0.069608 | 69 | 9253.5475
CUTTERS CT | WARREN ST | CARTER ST | 2024 | $2M Budget | Fair | Surface Treatment | 233.1303 | 0.044153 | 63 | 4108.7915
VIRGINIA LN | VIRGINIA LN-01 | STOREY BROOK RD | 2022 | $2M Budget | Fair | Surface Treatment | 349.1763 | 0.066132 | 70 | 13187.2267
ARTHUR WELCH | DANIEL LUCY WY | CUL DE SAC | 2023 | $2M Budget | Fair | Surface Treatment | 546.7444 | 0.10355 | 69 | 13765.8097
ARTICHOKE TER | STOREY AVE | DEAD END | 2023 | $2M Budget | Fair | Surface Treatment | 368.7375 | 0.069837 | 72 | 7427.1918
COOMBS CIR | NOBLE ST | CUL DE SAC | 2022 | $2M Budget | Fair | Surface Treatment | 641.1602 | 0.12143 | 68 | 19371.5883
DREW ST | PHILLIPS DR | HOYTS LN | 2023 | Drainage Bond | Poor | Surface Treatment | 384.5141 | 0.072825 | 43 | 0
| PHILLIPS DR | PHILLIPS DR | 2023 | Drainage Bond | Fair | Surface Treatment | 1026.8271 | 0.19447 | 62 | 0
DANIEL LUCY WAY | PINE HILL RD |  | 2023 | $2M Budget | Fair | Surface Treatment | 429.8844 | 0.081418 | 72 | 12988.2412
HOYTS LN | DANIEL LUCY WAY |  | 2023 | $2M Budget | Fair | Surface Treatment | 1078.0283 | 0.20417 | 72 | 32570.8297
EPPA WY | HIGH ST | POND ST | 2024 | $2M Budget | Fair | Surface Treatment | 176.223 | 0.033376 | 68 | 5767.9761
BASIN STREET | 76TH ST | 78TH ST | 2023 | $2M Budget | Good | Surface Treatment | 625.5834 | 0.11848 | 73 | 15750.7995
EPPA WY | HIGH ST | POND ST | 2024 | $2M Budget | Fair | Surface Treatment | 176.223 | 0.033376 | 68 | 5767.9761
ELMIRA AVE | MOSELEY AVE | FERRY RD | 2024 | $2M Budget | Fair | Surface Treatment | 1294.6994 | 0.24521 | 69 | 45636.716
[9 empty] | TOTAL | 1120165.3906